## Sheet1
Module | Function | Owner | to be tested by user / IS | Testing Platform | Remarks | Migration Impact | Pre-Migration Validation | Post-Migration Validation | Performance Benchmark | Security/Compliance Check | Rollback Plan
Care | Caring Service - PowerBank Rental |  |  |  |  | Uses Azure Blob for logs | Backup DB + blob | Local DB + log directory verified | Latency < 200ms | Local firewall allows service | Switch DNS back to Azure
Care | Caring Service - Content Transfer |  |  |  |  | Relies on Azure Storage | Backup storage account | File transfer works locally | Compare file copy speed | SSL cert installed | Restore Azure storage
Care | Bill Payment using QRCode |  |  |  |  | Depends on Azure SQL | Backup DB + schema export | API returns correct account data | Query < 1s | Local DB encryption enabled | Restore Azure SQL
Care | Caring Service - Remote Queue |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Account | Get account status(Main, sub) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Account | Get Voice mins |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Account | Data of Data used |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Account | Get Data Limit |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Account | Set Data Limit (Mobile Data Allocation ) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - App Launch | Checking app version |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Bill & Payment | Get Account Details ( Amount Due, Due Date, Payment Method) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Bill & Payment | Get Bill Statements |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Bill & Payment | Update Bill Statement Language |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Bill & Payment | My Documents Portal Password |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Bill & Payment | Get Document list |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - First Time Launch | [5 empty] | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Home | Get account details/Profile |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Home | Get Switch Account |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Home | Switch account function |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | Login with Account |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | Login with Phone number |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | Reset Password |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | Login with Bio |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | Check Login Session |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | set Bio Token |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Login | update Push notification token |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | Member teir |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | Member Voucher/Coupons status |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | Membership realtime QRCode |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | get Birthday Widget |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | get Promotions |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Membership | get Membership Offer Lists |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - My Plan | Get Plan Details |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - My Plan | Get Detail when China & HK 1 Card 2 Numbers applied |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - My Plan | get RNR Cert |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Retrieve the Profile information |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Update the Profile |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Retrieve My Interests info |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Update the Interests option |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Change Password |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Settings | Logout function |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - SIM Management | Set Call Forwarding |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - SIM Management | Set Voicemail Language |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Travel | Get Roaming plans dtails |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Travel | Get Roaming Data Used |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Widget | Get account data usage |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Widget | Get bill payment status |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Widget | Get roaming plan status |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
Care - Widget | Membership Spending |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - My Profile | Get account details |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - AutoPay | Get Autopay details ( maybe need to follow PCI, not showing and storing CC data ) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - AutoPay | Apply Credit Card Autopay |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Call Forwarding | Activate and Deactivate call forwarding number |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Communication | Get Accept or Reject for EDM |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Delivery Address | Get Account delivery address info |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Delivery Address | Add/edit/delete Delivery Address |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Home | Get Account Info |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Home | Get Smartone Membership Info |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Home | Get SubAccount info |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - LogInNow | Get account username details |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - LogInNow | Change or update Username |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - LogInNow | Change or update Password |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - My Orders | Get orders Info, current and completed |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - MyDocuments | Get account documents( Per sub account as well ) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - MyPlan | Get Plan details(only with main account, if its Family plan) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - MyRewards | Get Details of rewards with Asia Miles |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Overview | Get Account type(Family, Solo, etc) |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Payment Info | This page is blank, and UI error in that page, submenu jumped to Online store section |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - PaymentMethod | Redirect to the corp-webpage, not suppost to. |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - PayMyBill | Same as MyAccount Home page |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - SendSMS online | [5 empty] | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Statement | Get Statements from Account |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Update Profile | Update Profile details, like address, contact number, email preferred Language, and etc. |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount - Usage Details | Get account usage details |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount- Login | Login with password |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount- Login | Login with OTP |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment
MyAccount- Login | Forget password function |  |  |  |  | Check Azure dependencies (DB, Storage, API, Functions) | Backup databases, configs, and DNS records | Verify functionality on local server | Compare response times with Azure baseline | Verify firewall, certificates, access roles | Revert DNS/config to Azure environment